Spectra Migration Discovery Project

Contents

Document Management	5

Contributors	5

Version Control	5

Distribution	6

Approval	6

Introduction	7

Objectives	7

Out of Scope, Assumptions and Constraints	8

Out of Scope	8

Assumptions	8

Constraints	8

Hub-and-spoke network design	8

Migration Approach	11

Patient Portal	11

ETL Services	14

SpectraPM Application	17

Topcon Harmony	22

Instant Booking System (LU)	26

Path to Azure-Diagram	29

Spectra Key Component Mapping	30

Shared Azure Platform Services	34

Azure Routing Path	34

Storage Technical Consideration	35

External Communication Systems (Yakara, UKMail, MMG and Synertec	37

Disaster Recovery	38

Migration Strategy-Focus Area (Aligned to Spectra Programme Migration)	39

Phased Migration Plan (Programme-By-Programme Approach)	39

POC (Proof of Concept)	40

Temporary Hybrid Connectivity For Data Movement	41

Cutover Planning and Rollback Options	41

Cutover plan (per programme)	41

Rollback options	42

Testing and Validation Steps	42

Operational Model	44

Post-Migration Operations	44

Application Operations	44

Infrastructure Operations	44

Shared Services Operations	45

Monitoring and Alerting	45

Application Monitoring	45

Database Monitoring	46

Storage & File Monitoring	46

PACS/Harmony Monitoring	46

Networking / Security Monitoring	46

Backup and Disaster Recovery Strategy	47

Databases	47

Azure Files Premium (Image Store)	47

Harmony PACS (Azure VM)	47

App Services & Containers	48

DR Failover	48

Governance and Compliance Controls	48

Security & Access Control	48

Compliance Alignment	49

Configuration Governance	49

Operational Governance	49

Data Governance	49

Path to Live	50

Foundation Readiness (Platform Layer)	50

Proof of Concept (Vertical Slice)	50

Objectives	51

Non-Production Migration (Dev/Test)	51

Production Migration (Programme-by-Programme)	51

Proposed Migration Order	52

Deployment Validation:	52

Cutover Steps	52

Rollback	52

Post-Go-Live Stabilisation	53

Transition to Business-as-Usual (BAU)	53

Operational handover	53

DR & Resilience	53

Cost & Resource Optimisation	54

Final Migration Completion	54

# Document Management

## Contributors

| No | Name | Role |
| --- | --- | --- |
| 1 | Kamran Ahmed | DevOps/Cloud Infrastructure Engineer |
| 2 | Sarath C. Munugoti | Solution Architect |
| 3 | Ravindar Gavinolla | Platform Architect/Cloud Infrastructure Engineer |
| 4 | Chaithanya Kutnikar | Architect |
| 5 | Oladeji Odedele | Senior Delivery Manager |
| 6 | James Zwier | Solution Architect/Consultant |

## Version Control

| Version | Updated by | Description of Amendment | Date of Change |
| --- | --- | --- | --- |
| 1 | Sarath, Kamran, Ravi, Chaithan | 1st draft-1.0 | 10/11/25 |
| 2 | Sarath, Kamran, Ravi, Chaithan, Ola | Internal review 1 | 12/11/25 |
| 3 | Sarath, Kamran, Ravi, Chaithan, Ola | 2nd draft-1.2 | 14/11/25 |
| 4 | Sarath, Kamran, Ravi, Chaithan, Ola | Internal review 2 | 18/11/25 |
| 5 | James, Sarath, Kamran, Ravi, Chaithan, Ola | Internal review 3 | 20/11/25 |
| 6 | Kamran | 3rd draft-1.4 | 26/11/25 |
| 7 | Ravindar | LLD updated with target architecture- 1.6 | 26/11/25 |
| 8 | Ola | 4th draft -Formatting and further update-1.8 | 27/11/25 |
| 9 | James, Sarath, Kamran, Chaithan, Ola | Final internal review | 28/11/25 |
| 10 | InHealth Team | External review | 01/12/25 |

## Distribution

| Name | Role | Business Area |
| --- | --- | --- |
| James Zwiers | Principal Architect | Mastek |
| James Gray | Account Director | Mastek |
| Ian Chan | Head of IT | InHealth |
| Chris Sagar | Head of Platforms | InHealth |
| James Pickup | Principal Infrastructure | InHealth |
| Haydn Harrison | Head of Development & Testing | InHealth |
| Michael Morris | Principal Software Engineer | InHealth |
| Praveen Khard | Cloud Infrastructure Engineer | InHealth |
| Peter Dyke | Commercial Manager | InHealth |
| Andrew Frith | Director of Digital Transformation (screening) | InHealth |

## Approval

|  | Date | Notes |
| --- | --- | --- |

# Introduction

As part of the low-level design for the Spectra migration to Azure Cloud, our primary objective is to establish a robust, scalable, and secure infrastructure that aligns closely with the principles set out in the high-level design.

This involves implementing a hub-and-spoke network topology within Azure, ensuring that each programme or instance benefits from dedicated services such as site-to-site VPN connectivity, advanced network security through appliances like Palo Alto firewalls, managed DNS services, and centralised domain controllers. The design will be replicated for each instance, allowing for consistency and ease of management across the organisation.

Additionally, a proof of concept (POC) will be developed to validate the approach, ensuring that all workloads are optimally hosted and integrated within the existing Azure Landing Zone. This comprehensive low-level design will facilitate seamless migration, enhanced security, and operational efficiency for Spectra's cloud-based workloads.

# Objectives

This Low-Level Design (LLD) is complementary to the High-Level Design (HLD), and reference should be made to the HLD for overarching architectural principles and context. The LLD provides the detailed technical blueprint required to implement the strategic direction set out in the HLD, ensuring alignment throughout the migration process.

This Low-Level Design (LLD) represents the implementation of mostly Option B – Re-platforming and Option A- lift and shift, as defined in the strategic migration approach. By adopting these options, the architecture leverages Azure-native services and infrastructure to rehost and optimise Spectra workloads, ensuring improved scalability, security, and manageability throughout the migration process.

Each Spectra instance or programme will have its own dedicated services, and this architectural model will be replicated for every Spectra instance or programme. Additionally, a proof of concept (POC) will be developed based on this approach.

# Out of Scope, Assumptions and Constraints

## Out of Scope

Infrastructure-as-Code (IaC) such as Bicep templates, ARM templates, for this phase of the project.

- Azure DevOps Pipelines / CI-CD Pipelines for automated deployments are out of scope for the LLD and will be addressed in a separate delivery workstream if required.

- Pipeline definitions, repository structures, branching strategies, release processes, and YAML definitions are not included in this document.

## Assumptions

- Deployment of Azure resources will be performed manually using the Azure Portal, CLI, or scripts until IaC is introduced in a later phase.

- The application team will provide container images ready for deployment.

- Required Azure subscriptions, VNet, and firewall rules will exist before workloads are deployed.

- Networking (CIDRs, subnets) will be approved and allocated by the InHealth Infrastructure team.

- No GitOps, CI/CD, or automation dependencies exist for go-live.

## Constraints

Each Instance/programme has its own dedicated services, and this architecture will be repeated for each instance/programme. There will also be a POC based on this information.

Region: UK_South as primary, availability zone and availability sets enabled for high availability, UK_West as secondary Site (DR – Azure Site Recovery).

# Hub-and-spoke network design

Spectra workloads will be hosted in a hub-and-spoke topology aligned to the existing Azure Landing Zone. The central hub subscription contains.

- Virtual WAN for site-to-site VPN connections

- Network virtual appliance (Palo Alto Firewall)

- Azure DNS connections

- Domain Controllers

Subsequently there are four Spectra subscriptions.

- Prod Spectra - for production application resources

- Dev Spectra - for all non-production environments (dev, test, preproduction)

- Prod Spectra DMZ - for application gateways and WAFs directed to Prod Spectra

- Dev Spectra DMZ - for application gateways and WAFs directed to Dev Spectra

Each Subscription has its own virtual network (VNet) and these VNets are peered only with the hub subscription, forcing all the traffic between subscriptions to traverse the firewall.

Summary

- Internet & Public Access Layer

- Azure Front Door

  - Entry point for internet users

  - Provides global routing + WAF (Web Application Firewall)

- DMZ Hub

  - Uses Application Gateway (Layer-7 load balancer / WAF)

  - Azure Firewall for packet filtering + security policies

  - Traffic from Front Door enters here before internal network

- Hub and Spoke Model

- Hub – includes Firewall, Bastion, VPN gateway, Application Gateway, DMZ VNet

- Spoke- components includes Production Application VNet, Runtime Subnet, and Data Subnet as spoke Subnet

# Migration Approach

## Patient Portal

| Aspect | Detail |
| --- | --- |
| Current | • Two on-prem Linux VMs: Patient Portal Frontend (Java/Vue) and Patient Portal Backend (Java API) • Portal Image Service; Springboot microservice (Java) • Exposed to patients via HSCN / external network, uses NHS Login (OpenID Connect) for authentication • Backend talks to Spectra Lung Core Application via JSON REST API on another VM • Availability and scaling handled via local virtualisation (XenServer) and manual VM sizing • On-prem network; no VNet / Private Endpoint concepts |
| Refactor approach | Containerise both Java apps (frontend and backend) into separate Docker images. Second Option; Host portal front end as static site - Frontend; Azure App Services – Ideal for JS/Query SPA or multi-page app - Backend & Image Service; Azure App Service (Java) Given there are several java microservices (backend, portal image services etc) it is recommended to use Azure container apps • Deploy both as Web App for Containers into a single App Service Plan in the Patient Portal spoke VNet • VNet & subnets (InHealth to provide subnet details): - VNet: vnet-spectra-pprod– 10.133.128.0/20 - Subnet (App Gateway): snet-pp-appgw – 10.133.XX.XX/28 (dedicated for App Gateway v2/WAF) - Subnet (App Service VNet Integration): snet-pp-appsvc – 10.133.XX.XX/28 (delegated to Microsoft.Web/serverFarms for outbound VNet integration) - Subnet (Private Endpoints): snet-pp-privendpt – 10.133.XX.XX/28 (for PE resources used by the portal) • Frontend is internet-facing via Azure Application Gateway (WAF) in snet-pp-appgw • Backend app is internal-only – accessed by the frontend via VNet integration and private DNS; no public endpoint • Private Endpoints: - Private Endpoint for PostgreSQL/DB tier used by the portal into snet-pp-privendpt - Private Endpoint for KeyVault (secrets, certs) intosnet-pp-privendpt - Private Endpoint for Storage (ifportalusesblob/fileforimagesordocuments) - Optional Private Endpoint for ACR so AppService pulls images privately • Use autoscale rules on the App Service Plan (CPU/HTTP queue) and deployment slots for blue-green releases and zero-downtime deployments |
| Target Azure services | • Azure App Service (Linux – Web App for Containers) for: - app-pp-frontend (Java and Vue.js) - app-pp-backend (Java JSON API) • Azure App Service Plan (Linux) hosting both apps • Azure Container Registry (ACR – Basic) to store images, with Private Endpoint in snet-pp-privendpt • Azure Application Gateway v2 (WAF) in snet-pp-appgw as public entry point (no direct public access to App Service) • Azure Key Vault with Private Endpoint (secrets, NHS Login client secrets, certificates) • Azure Database (e.g. PostgreSQL Flexible Server) with Private Endpoint (if/where the Patient Portal has its own DB) • Private DNS zones for privatelink.* endpoints and App Service VNet integration names |
| SKU & sizing | • App Service Plan: Premium v3, P1v3 (Linux) – 2 vCPU, 8 GB RAM, 250 GB storage per worker • Instance count: 2 instances for HA and to handle patient concurrency • Both frontend and backend apps run on the same P1v3 plan, sharing the two workers • ACR: Basic tier (shared across containerised Spectra workloads) • App Gateway: WAF v2 (exact SKU sized in shared networking section) |
| Estimated cost (compute only, in £) | • App Service Premium v3 P1v3 is £190/month per instance • With 2 instances in the plan: £380/month for Patient Portal App Service compute • ACR (Basic) £4/month, shared across workloads (only a fraction attributable to the portal). ACR is entry-level tier of Azure Container Registry, offering 10 GB of storage and limited features, designed for small-scale projects • Private Endpoints: low per-hour cost each; multiple PEs (DB, KV, Storage, ACR) would typically be in the low tens of £/month and are captured in the shared networking/security cost model |
| Options and Justification | We have three realistic refactor options for the Patient Portal in Azure: 1. App Service for Containers (frontend and backend in one P1v3 plan), 2. Azure Container Apps 3. AKS For this project the recommended approach is App Service for Containers, it’s the simplest to operate, fully supports our container strategy, integrates cleanly with App Gateway/WAF and NHS Login, and will be cheaper and more predictable than running a full AKS cluster. Azure Container Apps is a good secondary option, especially for low-usage non-prod environments where scale-to-zero can reduce cost |

## ETL Services

| Aspect | Detail |
| --- | --- |
| Current | ETL consists of three components: 1. ETL Service – Java (Dropwizard), performs ingestion, validation, heuristics, data quality checks 2. ETL Web Portal – HTML-based, used by external practice users to upload/export practice data 3. ETL User Interface – JavaFX desktop application used by internal Customer Ops and Analytics teams to manage ETL jobs and handle complex data issues - ETL interacts with the Spectra PM PostgreSQL database, writing demographic and clinical coded data (SNOMED CT, Read2/3) - Data arrives from commissioners, GP systems (EMIS), GPSTRs, MESH queries, remote practice access, etc - Runs on on-prem Linux servers (multiple VM roles) - Scaling is manual, based on XenServer capacity - No Private Endpoints / VNet segmentation; accesses DB directly on-prem |
| Refactor approach | • Containerise ETL Service (Java Dropwizard) into a backend API container • Containerise ETL Web Portal into a lightweight frontend container (HTML/JS) • Deploy ETL Service and ETL Web Portal as Web App for Containers under a dedicated App Service Plan in the Production spoke VNet • Use Private Endpoints to connect securely to: - PostgreSQL Flexible Server (Spectra PM Database) - Storage Account (temporary file staging, GP2DRS exports) - Key Vault (connection strings, API secrets) - ACR (optional, for private container pulls) • Expose ETL Web Portal publicly via App Gateway (WAF) in DMZ subnet for practice users. (No longer used by External practice Users) • Keep ETL Service internal-only (no public endpoint), accessed via VNet integration and private DNS • Autoscale ETL Service based on CPU/queue length for heavy data load periods |
| Target Azure services | • Azure App Service (Linux – Web App for Containers) for: - etl-service-api (Java Dropwizard) • Azure Container Registry (ACR – Basic) for storing ETL containers • Azure PostgreSQL Flexible Server (with Private Endpoint) for ETL writes into the Spectra PM database • Azure Application Gateway v2 (WAF) as public entry point for ETL Web Portal • Azure Key Vault (with Private Endpoint) • Azure Storage Account for GP2DRS/CSV/XML temp ingest (with Private Endpoint; Blob storage) • Private DNS Zones for privatelink.postgres.database.azure.com, privatelink.vaultcore.azure.net, privatelink.blob.core.windows.net, etc • VNet & Subnets (InHealth to provide): - VNet: vnet-spectra-pprod – 10.133.128.0/20 - Subnet App Gateway: snet-etl-appgw – 10.133.XXX.XX/28 - Subnet App Service integration: snet-etl-appsvc – 10.133.XX.X/28 - (delegated to Microsoft.Web/serverFarms) - Subnet Private Endpoints: snet-etl-privendpt – 10.133.XX.X/28 |
| SKU & sizing | • App Service Plan: Premium v3, P1v3 (Linux) – 2 vCPU, 8 GB RAM, 250 GB storage per worker • Instance count: 2 instances – ETL load can spike, requires HA and parallel ingestion • Both ETL Service and ETL Web Portal run on the same P1v3 plan • PostgreSQL DB sizing (typical): Flexible Server General Purpose – 4 vCore for ETL throughput (size can be tuned per environment) • ACR: Basic tier • Storage: Standard Hot or Cool tier depending on ingestion volume Current on-prem ETL runs on a 16 vCPU / 96 GB shared VM (Apache and ETL). In Azure, ETL is split into containerised services and scaled horizontally on App Service (2× P1v3 to start). Actual workload is expected to use a fraction of the legacy VM capacity; sizing will be validated and right-sized during POC and non-prod performance testing |
| Estimated cost (compute only, in £) | • App Service P1v3 £190/month per instance • 2× P1v3 instances = £380/month for ETL compute • PostgreSQL Flexible Server (example GP 4 vCores): £160–£220/month depending on storage/IO profile • Private Endpoints (PE for DB, KV, Storage, ACR): £25–£40/month total • ACR Basic £4/month (shared) • App Gateway WAF v2 £150–£250/month (shared security infra, not attributed solely to ETL) |
| Brief summary | The ETL system is modernised by moving the ETL Service and ETL Web Portal into Azure App Service (Linux) as containerised workloads, running inside a dedicated ETL spoke VNet. The portal is accessed by external practice users via App Gateway/WAF, while the ETL Service remains internal-only. All platform services (PostgreSQL, Storage, Key Vault, ACR) use Private Endpoints to ensure data never leaves the private network. The architecture supports parallel processing, scaling during peak ingest periods, and secure upload of GP2DRS and clinical data into Spectra PM. |
| Options and Reason | 1.Azure App Service (Web App for Containers) 2. Azure Container Apps (ACA) 3. Azure Kubernetes Service (AKS) Option 1 (Azure App Service) is the best balance of cost, simplicity, security, and operational overhead. ETL needs to run continuously and integrate tightly with Private Endpoints, App Gateway and VNet, which App Service handles cleanly without the complexity or cost of AKS or ACA. |

## SpectraPM Application

| Aspect | Detail |
| --- | --- |
| Current | • Core Spectra PM is a monolithic PHP application with JavaScript frontend • Each screening programme operates as a separate instance, each with its own PostgreSQL database • Hybrid imaging model: - /retina images stored on a simple network file share (SMB) - OCT scans stored in TOPCON Harmony PACS • Batch/Background jobs: - Grading Manager – PHP CLI tool running every 30–60 mins to process screening results - System Manager – PHP CLI tool running overnight for recalls and status updates • Integration components: - PACS Integration Service (Java Spring Boot) connecting all programmes to Harmony PACS - Patient Portal (Java microservice) - ETL tool (demographics and clinical loading) - Spectra Client desktop application used by graders and screeners • External integrations: Yakara, UK Mail/Synertec, MMG (patient communications) • Entire platform hosted on-prem on Linux VMs and file servers; manual scaling; no segmentation or Private Endpoints |
| Refactor approach | • Containerise the PHP monolithic application (one image per programme) • Deploy one Web App for Containers per programme, matching current isolation (separate DB and image paths). • Containerise PACS Integration Service as a shared internal-only Java container service • Convert Grading Manager and System Manager into scheduled App Service background jobs or timer-triggered container runs • Migrate image storage to Azure Files Premium (SMB) with Private Endpoint • Maintain OCT workflow via Harmony PACS accessed through VWAN/VPN by PACS Integration Service • PostgreSQL per programme migrates to Azure PostgreSQL Flexible Server with Private Endpoint • Store all containers in Azure Container Registry (ACR – Basic) • Use Private Endpoints for: PostgreSQL, Azure Files, Key Vault, ACR • Implement blue/green deployments, VNet integration, and App Gateway routing where external access is required |
| Target Azure Services | Azure App Service (Linux – Web App for Containers) for: - spectrapm-core-<programme> (PHP monolith) • Shared internal App Service for: - pacs-integration-service (Java Spring Boot) • Scheduled jobs: - grading-manager (PHP CLI container) - system-manager (PHP CLI container) • Azure PostgreSQL Flexible Server (PE) – one per programme • Azure Files Premium (PE) - per-programme image store • Azure Container Registry (ACR – Basic) • Azure Key Vault (PE) • Private DNS Zones for all Private Endpoint integrations • VNet/subnets (example ranges): - vnet-spectra-pprod → 10.133.128.0/20 - snet-pm-appgw → 10.133.XX.XX/28 - snet-pm-appsvc → 10.133.XX.XX/28 - snet-pm-privendpt → 10.133.XX.XX/28 |
| SKU & sizing | • App Service Plan (Linux): Premium v3 – P2v3 (4 vCPU, 16 GB RAM) • 2× instances per programme for HA and image-heavy workload • PACS Integration Service: Premium v3 P1v3, 2× instances • Azure Files Premium: sized based on per-programme image volume and IOPS profile • PostgreSQL Flexible Server per programme: General Purpose 4–8 vCores • ACR Basic, Key Vault Standard, Private Endpoints, App Gateway WAF v2 (shared) |
| Estimated cost (compute only) | • App Service P2v3 £380/month per instance : £760/month per programme • PACS Integration Service (P1v3) £380/month total • PostgreSQL Flexible Server per programme: £160–£380/month depending on vCores • Azure Files Premium: £150–£300/month depending on provisioned size/IOPS • Private Endpoints: £25–£50/month per programme • ACR Basic: £4/month (shared) • App Gateway WAF v2: £150–£250/month (shared) |
| Summary | Spectra PM is refactored into Azure using a per-programme containerised PHP monolith model, each with its own PostgreSQL Flexible Server and Azure Files Premium SMB image share |
| Options and Justification | We have three realistic refactor options for the Spectra PM application in Azure: - App Service for Containers (one containerised PHP instance per programme on a P2v3 plan) - Azure Container Apps - AKS (Azure Kubernetes Service) For this project the recommended approach is App Service for Containers It provides the simplest operational model, requires minimal changes to the PHP monolith, supports the heavy SMB image workload via Azure Files Premium, integrates cleanly with private networking and Private Endpoints, and aligns with the current per-programme isolation model. It is also significantly easier and more cost-predictable than running PM in AKS. Azure Container Apps is a secondary option for non-production workloads where scale-to-zero may reduce cost. AKS is not recommended due to the high complexity and operational overhead required for a monolithic application. |

## Topcon Harmony

| Aspect | Detail |
| --- | --- |
| Current | • Topcon Harmony PACS Suite runs on a single on-prem Linux VM (Debian 13) • VM spec: 16 vCPU / 64 GB RAM • Storage layout: - PostgreSQL data: 60 GB - WADO cache: 550 GB (high I/O imaging cache) - Harmony app: 60 GB - Orthanc/DICOM store: 100 GB • OCT scans automatically uploaded into Harmony PACS • images stay in Spectra network file share (Spectra Image Store) • Clinicians context-launch from Spectra Client into Harmony to assess OCT images • PACS Integration Service (Java Spring Boot) is shared across all DESP programmes and mediates Spectra ↔ Harmony interactions • Harmony currently sits in the HSCN/DMZ-aligned network zone with private access only |
| Refactor approach | • Treat Harmony as a vendor PACS appliance: lift-and-shift to Azure first (IaaS), then optimise if Topcon supports cloud-native patterns • Deploy Harmony on Azure Linux VM(s) with the same compute profile (16 vCPU / 64 GB) • Split disks to match workload and use high-performance tiers for cache and DICOM store • Place Harmony in a dedicated PACS/Imaging spoke VNet, private-only, reachable from Spectra spokes via the hub/VWAN • PACS Integration Service remains a shared internal service in Azure and talks to Harmony over private Ips • Spectra Clients continue to context-launch to Harmony via private DNS name over HSCN/VPN/VWAN (no public endpoint). • Keep OCT scans in Harmony; keep in Azure Files (Spectra Image Store) as per Spectra PM design. |
| Target Azure services | Compute • Azure Virtual Machines (Linux) for Harmony PACS Suite. • Availability Zones / Availability Set for resilience (depending on Topcon support). • Azure Standard Load Balancer (internal) only if Topcon supports active/active or active/passive nodes. Storage • Azure Managed Disks attached to Harmony VMs: - OS disk (Premium SSD) - PostgreSQL disk (128 GB Premium SSD) - wadocache disk (1 TB Premium SSD v2 / Ultra depending on IOPS needs) - Orthanc/DICOM disk (256–512 GB Premium SSD v2) • Azure Backup for VM and disk backups (with Topcon-approved schedule) Networking & Security • Dedicated PACS Spoke VNet (example) vnet-spectra-pprod 10.133.128.0/20 Subnets - snet-pacs-app – 10.133.XX.XX/28 (Harmony VMs) - snet-pacs-mgmt – 10.133.XX.XX/28 (admin/jump/AVD access if needed) • Hub/VWAN peering to Spectra programme spokes and HSCN ingress path • Azure Firewall / NVA routing enforced via hub for all outbound and inter-spoke flows • Private DNS zone for Harmony FQDN (e.g.harmony.internal.spectra.local) • Log Analytics and Azure Monitor / Defender for Cloud for logging, VM vulnerability mgmt, alerts Shared Integration • PACS Integration Service hosted in Azure (as already defined): App Service for Containers (internal-only) with VNet integration. It uses private routing to Harmony |
| SKU & sizing | Harmony VM SKU (baseline like-for-like): • Standard D16s v5 (16 vCPU, 64 GB RAM) or closest NHS-approved equivalent Disk tiers (baseline): • OS: Premium SSD P30 (1 TB max tier, sized smaller as needed) • PostgreSQL: Premium SSD P10/P15 (128 GB) • WADO cache: Premium SSD v2 with provisioned IOPS/throughput sized for peak OCT viewing (start 1 TB) Orthanc/DICOM: - Premium SSD v2 (256–512 GB) Resilience: • Start with single node (lift/shift). Add second node in another AZ if Topcon supports clustering/replication |
| Estimated cost (high level, £) | • 1× D16s v5 VM typically lands in the mid-hundreds £/month range (exact region pricing to be confirmed) • Premium SSD v2 / Ultra cache disk will be one of the larger cost items depending on IOPS/throughput provisioning • Overall Harmony cost will be driven by cache and DICOM storage performance, not CPU |
| Brief summary | Harmony moves to Azure as a private PACS appliance in its own Imaging spoke. It runs on a like-for-like Linux VM with high-performance managed disks for PostgreSQL, WADO cache, and Orthanc/DICOM storage. OCT scans continue to land in Harmony, while images remain in Spectra’s Azure Files image store. Clinicians still context-launch from Spectra Client to Harmony through private DNS over HSCN/VWAN, and the shared PACS Integration Service connects all programmes to Harmony using private VNet routing. |
| Options and Justification | We have three realistic options for Harmony PACS in Azure: - Lift-and-shift to Azure Virtual Machines (like-for-like Linux VM with Premium SSD v2/Ultra disks) - Refactor to a vendor-hosted/cloud Harmony service (if/when Topcon offer and support it) - Re-engineer PACS to native Azure services (custom PACS) For this project the recommended approach is lift-and-shift to Azure Virtual Machines. Harmony is a vendor PACS appliance; keeping it on an IaaS VM preserves vendor support, allows us to use high-performance disks for OCT/Wadocache workloads, and minimises change risk for clinicians. A cloud-native Harmony offering can be considered later if Topcon formally support it, while a full PACS re-write is out of scope for this programme. |

## Instant Booking System (LU)

| Aspect | Detail |
| --- | --- |
| Current | This refers to the Lung Cancer Screening Instant Booking Service (separate from DESP Patient Portal booking) Components shown in diagrams: - Instant Booking Middleware – Java Spring Boot microservice (REST API) - Instant Booking Service Web Interface – HTML / Vue.js frontend - Apache front end currently used to serve the web UI / reverse proxy to middleware • Integrated to Spectra Lung Core Application via JSON REST API for booking operations, lifecycle, and reporting • Authentication model is lightweight: patients get a booking link via SMS and verify by selecting the correct DOB from options (no NHS Login) • Hosting today: 3 small on-prem Linux VMs (from spec): - Apache and Instant Booking Middleware: 2 vCPU / 4 GB / 30 GB disk - Instant Booking Middleware (app only): 2 vCPU / 4 GB / 30 GB disk - Apache (Instant Bookings Middleware Frontend): 2 vCPU / 4 GB / 30 GB disk • External users never connect directly to Spectra Lung Core; middleware protects core app |
| Refactor approach | • Containerise both Instant Booking components: - Middleware (Java Spring Boot) as container image - Web Interface (Vue.js static build) as container or static site (see options) • Replace Apache VM roles with managed ingress: - Frontend published through Azure Application Gateway (WAF) - Backend exposed internally only with no public endpoint • Deploy both containers on Azure App Service (Linux – Web App for Containers) within a dedicated Instant Booking spoke VNet • Networking (example ranges): - VNet: vnet-spectra-pprod – 10.133.128.0/20 - Subnet (App Gateway): snet-book-appgw – 10.133.XX.XX/28 - Subnet (App Service VNet Integration): snet-book-appsvc – 10.133.XX.XX/28 (delegated to Microsoft.Web/serverFarms)– Subnet (Private Endpoints): snet-book-privendpt – - 10.133.XX.XX/28 • Private Endpoints used where platform services are consumed: - Key Vault PE (secrets, SMS link signing keys, API creds) - Storage PE (if booking links/templates/exports are stored) - Optional ACR PE for private image pulls • Spectra Lung Core stays private in its own programme; Instant Booking talks to it over hub-transited private routing via Palo Alto/NVA • Autoscale middleware based on CPU/HTTP queue during booking peaks |
| Target Azure services | • Azure App Service (Linux – Web App for Containers) for: - instant-booking-frontend (Vue.js web UI) - instant-booking-middleware (Java Spring Boot API) • Azure App Service Plan (Linux) hosting both apps • Azure Container Registry (ACR – Basic) to store Booking containers (shared across Spectra) • Azure Application Gateway v2 (WAF) as the only public entry point for patients • Azure Key Vault (Private Endpoint) for secrets and signing keys • Azure Storage Account (Private Endpoint) if required for file staging/exports/templates • Private DNS Zones for all privatelink.* resources and internal name resolution • Hub/VWAN and Palo Alto firewall provides inspected private routing to Lung Core and other internal systems |
| SKU & sizing | • Hosting requirement today is lightweight (3× 2vCPU/4GB VMs) Equivalent Azure PaaS baseline: • App Service Plan (Linux): Premium v3 – P1v3 - 2 vCPU, 8 GB RAM per worker (comfortably covers current load) • Instance count: 2 instances for HA (patients booking is external facing) • Both frontend and middleware share the same plan • App Gateway: WAF v2 (shared DMZ cost model) • ACR Basic (shared), Key Vault Standard |
| Estimated cost (compute only, in £) | • App Service P1v3 £190/month per instance • 2× instances = £380/month for Instant Booking compute • ACR Basic £4/month shared • Private Endpoints (KV, Storage, optional ACR): low tens of £/month, captured in shared networking/security model • App Gateway WAF v2 cost sits in DMZ shared layer |
| Brief summary | The Lung Instant Booking Service is moved to Azure as two containerised apps (Vue.js frontend and Java Spring Boot middleware) running on a shared App Service Plan inside a dedicated Booking spoke VNet. Patients access only through Application Gateway WAF, while the middleware remains internal-only and talks privately to the Spectra Lung Core API through hub-inspected routing. This preserves the current security model (core not exposed) while removing the need for Apache and small Linux VMs. |
| Options and Justification | There are three realistic refactor options for the Instant Booking service in Azure: - App Service for Containers (frontend and middleware on one P1v3 plan) - Azure Container Apps - AKS. For this project the recommended approach is App Service for Containers. It is straightforward to run the Vue.js frontend and Java middleware as containers, integrates neatly with App Gateway/WAF, provides predictable cost for an external-facing service, and keeps the Lung Core API internal via VNet integration. Azure Container Apps is a good secondary option for non-prod, while AKS would add unnecessary operational overhead. |

# Path to Azure-Diagram

The diagram outlines a cloud migration and production architecture for the program.

- The architecture shows the migration of systems from on-premises infrastructure into Azure using Azure Migrate for Spectra and Patient portal Applications.

- Multiple Azure production resource groups are defined, each hosting different Spectra and Patient portal application components, APIs, data services, and integration tools.

- Spectra and Patient portal Application workloads include App Services, container environments, databases, API Management instances for Third part services like ((Yakara, UKMail, MMG, Synertec), and storage accounts for Letters and Image Processing.

- A dedicated data resource group supports file storage and database services used by the migrated Letter and image processing applications.

- Monitoring and analytics are handled through a separate resource group containing monitoring, logging, and API-related services.

- All production resource groups connect to a central Shared Services layer, which provides common functions such as ETL processing and Harmony shared resources.

- The overall design provides clear separation of roles and responsibilities across Spectra and Patient portal application, data, monitoring, and shared service layers within the Azure environment.

# Spectra Key Component Mapping

| Spectra component | Type | Scope | Target Azure service(s) | Notes / key dependencies | Name of the Component |
| --- | --- | --- | --- | --- | --- |
| Spectra PM Core (Monolithic PHP and JS) | Application | Per programme/instance | Azure App Service (Linux – Web App for Containers) on Premium v3 plan (P2v3) | One Web App per programme; compute isolated per programme if you keep separate plans. | Capp-prd {programm name}-spectra-desp-app-00 |
| Spectra PM PostgreSQL DB | Database | Per programme/instance | Azure PostgreSQL Flexible Server (GP 4–8 vCores) and Private Endpoint | One server per programme to preserve current isolation. | pgs-prd {programm name}-spectra-desp-db-00 |
| Spectra PM Image Store (SMB share) | Storage | Per programme/instance | Azure Files Premium (SMB) and Private Endpoint | High IOPS filesystem workloads; private only. | saprd {programm name}desp00 |
| Grading Manager (PHP CLI every 30–60 mins) | Background job | Per programme/instance | App Service background job / scheduled container on same PM plan | Timer/schedule controlled per programme. | lapp-prd {programm name}-spectra-desp-00 |
| System Manager (overnight PHP CLI) | Background job | Per programme/instance | App Service background job / scheduled container on same PM plan | Runs private; no inbound exposure. | lapp-prd {programm name}-spectra-desp-app-01 |
| PACS / PACS Integration Service (Java Spring Boot) | Integration service | Shared across programmes | Azure App Service (Linux – Web App for Containers) on Premium v3 plan (P1v3) and VNet integration | One shared internal service used by all DESP programmes. | apim-prd- {programm name} - desp-app-00 |
| Topcon Harmony PACS Suite | Vendor PACS | Shared | Azure Linux VM (D16s v5) and Premium SSD v2/Ultra disks | Lift-and-shift only (vendor supported). In PACS spoke VNet. | VMR.00 |
| Harmony PostgreSQL store | DB (vendor embedded) | Shared | Managed disks on Harmony VM | Not replatformed to PaaS (breaks support). | Msql-prd- shared-desp-db-01 |
| Harmony WADO cache / Orthanc DICOM store | Imaging storage | Shared | Premium SSD v2 / Ultra managed disks | Performance-driven sizing. | saprd {p-rogramm name} despfs01 |
| Patient Portal Frontend (Java/Vue) | Application | Per programme/instance (external) | Azure App Service (Linux – Web App for Containers) on P1v3 plan | Public only via App Gateway WAF; no direct public endpoint. | lapp-prd {programm name}-spectra-desp-app-00 |
| Patient Portal Backend (Java Spring Boot API) | API service | Per programme/instance (internal) | Azure App Service (Linux – Web App for Containers) on same P1v3 plan | Private only; called by frontend. | apim-prd {programm name}-spectra-desp-app-00 |
| Portal Image Service (Spring Boot) | Microservice | Per programme/instance | Azure App Service (container) on same P1v3 plan | Private only; uses storage/DB via PE if needed. | capp-prd {programm name}-spectra-desp-app-00 |
| Instant Booking Frontend (Vue.js) | Application | Per programme/instance (Lung) | Azure App Service (Linux – Web App for Containers) on P1v3 plan | Separate from DESP portal. Public only via App Gateway WAF. | capp-prd {programm name}-spectra-desp-app-00 |
| Instant Booking Middleware (Java Spring Boot) | API service | Per programme/instance (Lung) | Azure App Service (Linux – Web App for Containers) on same P1v3 plan | Private only; talks to Lung Core API. | capp-prd {programm name}-spectra-desp-app-00 |
| ETL Service (Java Dropwizard) | Data ingestion service | Shared (writes per-programme DBs) | Azure App Service (Linux – Web App for Containers) on P1v3 plan | Internal-only; autoscale for load spikes. | sdb-prd shared-spectra-desp-db-00 |
| ETL Web Portal (HTML) | Web UI | TBC / likely retired | Remove from build OR internal Web App | If no longer used externally, don’t publish via WAF |  |
| ETL JavaFX Desktop UI | Client tool | Shared internal users | Replace with internal web admin on App Service OR access via AVD | If replaced, becomes etl-admin-ui Web App | capp-prd shared-spectra-desp--00 |
| Spectra Lung Core Web Interface (PHP) | Application | Per programme/instance | Azure App Service (Linux – Web App for Containers) (plan to match PM isolation) | Not fully detailed earlier but same pattern as PM core | capp-prd {programm name}-spectra-desp-app-00 |
| Spectra Lung PostgreSQL DB | Database | Per programme/instance | Azure PostgreSQL Flexible Server and PE | Isolated per programme | pgs-prd {programm name}-spectra-desp-db-00 |
| Spectra Clients (desktop app for screeners/graders) | Thick client | Per programme/instance | No Azure hosting (endpoint-managed) | Remains installed on clinic devices; connects privately to Azure apps | TBC |
| Web Based Grading (planned replacement) | Application | Per programme/instance | Azure App Service (Linux – Web App for Containers) | Internal-only initially; later may replace desktop clients. | capp-prd {programm name}-spectra-desp-app-00 |
| NHS Login | External IdP | Shared external | External service | Integrated via OIDC to Patient Portal only. | APIM-prd-shared-spectra-desp--00 |
| Entra ID (OIDC) | Identity | Shared | Microsoft Entra ID and Conditional Access | Used by PM apps and internal users. |  |
| Yakara / UK Mail / Synertec / MMG | External comms | Shared | Outbound via Hub Palo Alto / Azure Firewall NAT | No inbound from internet; allow-list destinations. | APIM-prd- {programm name} -spectra-desp--00 |
| GP systems / GPSTRs / EMIS / MESH / Spine PDS | External data feeds | Shared | Inbound over HSCN/VWAN → ETL Service | ETL handles validation/heuristics before DB writes. | TBC |

# Shared Azure Platform Services

| Platform capability | Azure service(s) | Scope / notes |
| --- | --- | --- |
| Container image storage | Azure Container Registry (Basic) and optional PE | Shared across Spectra workloads |
| Public ingress / WAF | Azure Application Gateway v2 (WAF) in DMZ subscriptions | One per exposed workload group (Portal, Instant Booking, etc.) |
| Private networking | Spoke VNets and hub peering and VWAN and Palo Alto NVA | All inter-spoke traffic via firewall |
| Private access to PaaS | Private Endpoints and Private DNS zones (hub-hosted) | DBs, Files, Storage, KV, ACR |
| Secrets & certificates | Azure Key Vault (Standard) and PE | NHS Login secrets, DB creds, API keys |
| Logging / monitoring | Log Analytics Workspace and Azure Monitor and Defender for Cloud | Shared; per-programme workspaces optional |
| SIEM / correlation | Microsoft Sentinel | Shared SOC/central monitoring |
| Backups | Azure Backup (VMs, Files) and DB native backups | Harmony via VM backup; PaaS DB backups native |

# Azure Routing Path

| Source | Destination | Path | Firewall | Notes |
| --- | --- | --- | --- | --- |
| Patient (internet) | Portal Frontend | Internet → WAF → Palo Alto → snet-pp-appsvc | Yes | No direct App Service public access |
| HSCN GP/Clinic | Spectra PM | HSCN → VWAN → Hub → Palo Alto → PM subnet | Yes | TCP 443 only |
| Portal Backend | PM API | VNet Integration → Palo Alto → PM subnet | Yes | Private DNS resolution |
| PACS Integration | Harmony VM | PM subnet → Palo Alto → PACS subnet | Yes | Private-only |

# Storage Technical Consideration

There are significant concerns around latency when accessing PACS imaging data, particularly OCT scans and historical studies that require fast, consistent retrieval during clinical review. Although Azure Blob Storage can technically store large imaging datasets, it operates as object storage and therefore introduces higher and more variable latency, slower random reads, and lacks the POSIX-style file-system behaviours typically required by PACS viewers.

These limitations may negatively impact the Harmony PACS workflow, leading to reduced clinical performance or compatibility issues.

Blob Storage does offer advantages such as low cost, massive scalability and lifecycle tiering (Hot/Cool/Cold), but it carries risks in this context that must be carefully considered.

To mitigate these limitations, the recommended approach is to keep the primary PACS data on high-performance Azure Files Premium or VM-attached Premium SSD v2/Ultra disks and use Blob Storage only as a secondary long-retention store where slower retrieval times are acceptable.

| Area | Detail |
| --- | --- |
| Client Concerns | • Latency when accessing OCT and historical PACS images • Consistent throughput needed for clinical review • Compatibility with Harmony PACS workflows • Large dataset size (220 TB and 20 TB/yr growth) |
| Using Azure Blob Storage (Hot/Cool/Cold) | Pros: • Low storage cost • No practical size limit • Ability to tier data (Hot/Cool/Cold) • Good for long-term retention Cons: • Higher and inconsistent latency • Poor random-read performance vs file storage • Not suitable for DCOM viewers without re-engineering • Transaction costs for frequent access • No native POSIX file semantics required for PACS |
| Recommendation | • Do NOT use Blob as the primary PACS store. • Use Azure Files Premium or VM-attached Premium SSD v2/Ultra disks for low-latency clinical access. • Use Blob Storage (Cool/Cold) only as a secondary archival layer for 7and year historical data where slower retrieval is acceptable. Using Hot/premium storage for all will significantly increase the costs. |
| Scaling Options if Blob Is Not Fit for Purpose | • Scale Harmony VM disks vertically (larger Premium SSD v2 or Ultra configurations). • Add multiple Premium disk volumes and stripe (LVM/RAID) for higher throughput. • Expand Azure Files Premium shares per programme or per year to distribute IOPS load. • Separate “hot imaging” (recent years) onto highest-performance disks while shifting older images to lower-cost tiers. |

# External Communication Systems (Yakara, UKMail, MMG and Synertec

Spectra integrate with several external communication providers that support SMS notifications, appointment reminders, and letter-printing workflows. These services operate entirely outside the Spectra Azure environment and do not require inbound connectivity to Azure; instead, Spectra applications send outbound calls (API or file-based) to the vendor endpoints. All outbound traffic will continue to traverse the hub > NVA/firewall > internet path to maintain security controls and logging.

| External System Summary |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| External System | Purpose | How Spectra Uses It Today | Integration Behaviour | Azure Considerations | Notes from Transcript |
| Yakara | Hybrid SMS/Web appointment reminder service | Spectra sends a list of patients; Yakara sends SMS with confirmation link (“Are you still planning to attend? Yes/No”) | Likely REST API or secure file transfer based on batches | Outbound HTTPS from Spectra PM/ETL/Patient Portal via Azure Firewall; no private connectivity; no inbound rules | Used to improve attendance rates; classed as a "miscellaneous external system" |
| UK Mail | Letter printing and postal delivery | Spectra sends letter batches for print & postage (DISP likely still uses UK Mail) | Typically, SFTP file drop or API | Outbound-only traffic; storage staging via Azure Files or Blob; Azure Logic Apps can orchestrate | legacy; may still be used for DESP |
| MMG | SMS provider (current for DESP/Lung) | Used for booking confirmations, appointment reminders, call-centre confirmation texts (“If you ring the bookings office…”) | REST API (SMS gateway) | Outbound HTTPS; store API keys in Key Vault; use Managed Identity for secure retrieval | MMG now as SMS provider |
| Synertec | Letter printing & postal service (Lung programme) | Lung screening appears to use Synertec instead of UK Mail | SFTP, API or file-based | Outbound HTTPS/SFTP; can use Azure Logic Apps SFTP connector | Synertec - Used LU |

# Disaster Recovery

| Component | DR Method | Region | RTO | RPO |
| --- | --- | --- | --- | --- |
| PM | Rehydrate App Service, restore DB, restore Files | UK West | 4h | 15m |
| Portal | Rehydrate App Service, bring up App Gateway DR | UK West | 1–2h | 15m |
| Booking | Same as portal | UK West | 1–2h | 15m |
| ETL | Restore DB, rehydrate App Services | UK West | 4h | 15m |
| PACS | Azure Backup + manual restore; no multi-AZ unless vendor support | UK West | 24h | ≥15m |

# Migration Strategy-Focus Area (Aligned to Spectra Programme Migration)

## Phased Migration Plan (Programme-By-Programme Approach)

The migration will follow a controlled, programme-by-programme sequence, ensuring isolation is maintained and that no shared services are disrupted.
The recommended order is:

- Proof of Concept (POC) environment

  - Deploy single programme slice: Patient Portal > Spectra PM > ETL >PACS Integration > Harmony (test data only).

  - Validate networking, Private Endpoints, App Gateway WAF, container hosting, image storage (Azure Files Premium), DB performance.

- Non-production environments per programme

  - Migrate dev/test for Lung and DESP programme instances.

  - Containerised services deployed to App Service Plans.

  - Database migration to PostgreSQL Flexible Server.

  - Azure Files Premium provisioning for storage.

- Programme-by-programme production cutovers
Recommended order:

  - Lung (Instant Booking and Lung Core) – fewer shared dependencies, simpler flows.

  - DESP PM Instances (multiple programmes) – repeatable pattern per instance.

  - Patient Portal (DESP) – after PM instance and DB migration.

  - PACS Integration Service (shared) – migrate once all dependent programmes are ready.

  - Topcon Harmony PACS – Lift-and-shift once integration layer is proven and OCT test dataset validated.

- Shared services migration last

  - Log Analytics, Sentinel routing, ACR consolidation, shared Key Vault, shared Private DNS zones.

This approach minimises risk by ensuring each programme can be validated independently.

# POC (Proof of Concept)

The POC will validate the full Azure reference architecture on a single vertical slice:

- Containerised Spectra PM (PHP)

- Azure PostgreSQL Flexible Server

- Azure Files Premium ( images)

- Containerised Patient Portal

- Containerised Instant Booking (if needed)

- ETL Service deployed in App Service

- PACS Integration Service (Java) container

- Simulated access to Harmony PACS VM (small test VM, no production data)

- App Gateway and WAF

- End-to-end private routing (Hub → Spokes → PE → DB → Storage)

- Logging > Log Analytics (monitoring)

- Secrets > Key Vault

- Private DNS resolution

- End-to-end smoke tests (Portal ↔ PM ↔ DB ↔ ETL ↔ PACS Integration ↔ Harmony)

- Performance Testing

- DR Testing

- Back and Restore

Successful POC completion defines the template for all programmes.

# Temporary Hybrid Connectivity For Data Movement

Migration requires temporary secure hybrid connectivity between on-premises Middlewich/Chelmsford and Azure.
This will be handled using:

- Existing site-to-site VPN via Azure VWAN into the hub

- Routing enforced through Palo Alto NVA for traffic inspection

- Temporary Hybrid mode for:

  - File migration from SMB > Azure Files Premium

  - PostgreSQL migration will use Azure Database Migration Service (once Azure Migrate is configured) where possible; otherwise, pg_dump/pg_restore with controlled downtime. SMB shares will be migrated via AzCopy/robust copy tools into Azure Files Premium

  - Harmony PACS lift-and-shift (disk upload or rsync/robust copy)

  - ETL data source ingestion validation

  - Spectra Client validation from on-prem clinics

- Once all migrations complete, hybrid connectivity is reduced back to normal operations.

Hybrid mode ends once each programme’s data and application state has been fully tested in Azure.

# Cutover Planning and Rollback Options

Each programme will follow a controlled cutover process with rollback available at each phase.

## Cutover plan (per programme)

- Freeze writes on-prem (short downtime window).

- Final DB sync > PostgreSQL Flexible Server.

- Final SMB > Azure Files Premium delta sync.

- Switch DNS / connection strings to Azure.

- Bring Azure services live (App Service, PEs, WAF routing).

- Perform post-cutover verification tests.

- Decommission or archive old VMs.

## Rollback options

- Rollback DNS and traffic routing back to on-prem.

- Re-enable on-prem PostgreSQL DB as the authoritative source.

- Revert to legacy web endpoints (Portal, PM).

- For Harmony PACS failure: revert to on-prem VM snapshot using on-prem hypervisor.

- Rollback window kept open for each programme until “stable for 48 hours”.

Rollback is fast because migrations are parallel but switchovers are atomic per programme.

## Testing and Validation Steps

Each migrated programme will undergo structured validation before go-live:

1. Functional validation

- Patient Portal > Login (NHS Login for DESP only) > results view > bookings (DESP).

- Instant Booking > access via SMS link > booking flow > DOB verification (Lung).

- Spectra PM > grading workflow > recalls > admin tasks.

- ETL > load GPSTRs / test extracts > validate demographic/clinical ingestion.

- PACS Integration > retrieval of OCT images from Harmony > context launch.

- Spectra Client > connectivity test to Azure APIs.

2. Data validation

- Row counts between on-prem and Azure DBs.

- Image validation: number of files and checksum match for  images.

- OCT test dataset available in Harmony Azure VM.

- Integrity checks for GP2DRS/ETL files.

3. Performance & scaling tests

- App Service autoscale triggers.

- DB performance baseline vs on-prem.

- Azure Files Premium IOPS test for grading image access.

- WAF throughput tests for peak Portal/Booking usage.

4. Security validation

- Private Endpoint access only (no public DB/Storage).

- NSG and Firewall inspection paths confirmed.

- Key Vault secret rotation working.

- App Gateway WAF rules operational.

5. User acceptance testing (UAT)

- Programme teams validate full workflow.

- Clinical safety tests for grading, booking and OCT viewing.

- “Go/No-Go” checkpoint.

# Operational Model

## Post-Migration Operations

After migration, the Spectra workloads will transition into the Azure operational model, with responsibility split between InHealth technical team, this consists of Infrastructure, Application / developers, testing and the product team.

## Application Operations

- All Spectra application components (PM, ETL, Patient Portal, Instant Booking, PACS Integration Service, PM background jobs) run as App Service (Web App for Containers) or scheduled container tasks.

- Standard operating tasks include:

  - Managing deployment slots and blue/green releases

  - Performing zero-downtime updates to containers

  - Patch management for container base images

  - Updating environment variables, Feature Flags, Key Vault references

  - Managing per-programme App Service plans (capacity, scaling)

## Infrastructure Operations

- Azure Landing Zone manages:

  - Hub connectivity (VWAN, VPN)

  - Firewalls (Palo Alto), and route tables

  - NSGs are not applied to the Private Endpoint or App Service subnets. Instead, each subnet has a dedicated route table that forces all outbound and east–west traffic to the Palo Alto firewalls via the Azure Load Balancer in the ih-hub vNet

  - Private DNS zones and Private Endpoints

  - App Gateway WAF operation, certificates, and endpoint policies

  - Subnet capacity and VNet peerings

  - ACR policies, image retention, and scanning

- Harmony PACS VM operations include:

  - OS patching via Azure Update Manager

  - Disk and performance monitoring

  - Vendor-supported application updates

  - Attended maintenance windows (as per Topcon requirements)

## Shared Services Operations

- Log Analytics workspace management

- Key Vault secret rotation (NHS Login, SMS link signing, API keys)

- Sentinel rules and SOC triage

- Backup vault operations

- Storage tiering / lifecycle management for Azure Files

# Monitoring and Alerting

All monitoring is consolidated into the central Log Analytics/Sentinel environment defined in the existing Landing Zone.

## Application Monitoring

Applied to: Spectra PM, ETL, Patient Portal, Instant Booking, PACS Integration Service.

- Azure Monitor Application Insights for:

  - Request/response metrics (latency, 5xx/4xx)

  - Dependency tracking to DBs, Storage, external APIs (NHS Login, MMG, Synertec)

  - Container crash loops or memory pressure

  - Autoscale events on App Service plans

  - Availability tests for external endpoints (Portal, Booking UI)

- App Service Diagnostics and Log Streaming for per-app troubleshooting.

## Database Monitoring

- PostgreSQL Flexible Server metrics:

  - CPU, memory, connections, deadlocks

  - Slow query logging

  - Storage growth and IOPS

- Integrations with Application Insights dependency telemetry.

## Storage & File Monitoring

- Azure Files Premium:

  - IOPS throughput

  - SMB latency (important for grading workflows)

  - Capacity alerts

## PACS/Harmony Monitoring

- VM-level diagnostics: CPU, disk queue, IO throughput

- Log Analytics agent (AMA) for syslog, FS warnings, PostgreSQL alerts

- Optional custom heartbeat endpoint via PACS Integration Service

## Networking / Security Monitoring

- App Gateway WAF alerts (SQLi, XSS, bot mitigation)

- Firewall logs (Palo Alto → Sentinel)

- VNet flow logs for troubleshooting Private Endpoint routing

- Private DNS resolver logs

- Defender for Cloud recommendations (CIS/NCSC alignment)

# Backup and Disaster Recovery Strategy

## Databases

- PostgreSQL Flexible Server handles automatic backups:

  - 7–35 day retention (programme-specific)

  - Point-in-time restore (PITR) for ≤ 5 minutes granularity

  - Backups stored in geo-redundant storage (if opted)

## Azure Files Premium (Image Store)

- File share backup via Azure Backup for Azure Files

  - Daily snapshots

  - Long-term retention as required

  - Soft delete and share-level snapshotting

## Harmony PACS (Azure VM)

- Backed up using Azure Backup for VMs

  - Application-consistent snapshots if Topcon supports it (else crash-consistent)

  - Multiple vault retention policies

- Disk-level restore for Orthanc/DICOM and  wadocache supported

- DR strategy depends on vendor capability:

  - Currently single-node deployed, with optional warm-standby or replicated disks in secondary region (if supported).

## App Services & Containers

- No VM backups required.

- Resilience handled by:

  - Deployment slots (rollbacks)

  - ACR image versioning

  - Configuration stored in Key Vault

## DR Failover

- For programme workloads, DR is achieved by:

  - Restoring DBs into DR region

  - Rehydrating container apps in DR App Service plan

  - Using secondary region App Gateway

  - Restoring Files Premium to secondary region

- Harmony PACS remains a special case due to vendor constraints; separate failover runbook prepared.

# Governance and Compliance Controls

## Security & Access Control

- Access to all Azure resources controlled via Entra ID with RBAC:

  - Principle of least privilege (PoLP) enforced

  - No local/shared accounts in Spectra applications

  - ACR, Key Vault, DBs and Storage accessible only through Private Endpoints, not public endpoints

- Conditional Access and MFA enforced for admin operations.

## Compliance Alignment

Aligned with:

- NHS Digital / NHS England cloud hosting requirements

- NCSC Cloud Security Principles

- UK GDPR (patient-identifiable clinical data)

- Cyber Essentials Plus

## Configuration Governance

- Azure Policy used to enforce:

  - No public IPs on compute

  - Mandatory Private Endpoints for DB/Storage

  - Allowed VM sizes

  - Mandatory diagnostics and log collection

  - Encryption at rest enabled on all storage

- Blueprint / Landing Zone governance already applied across the hub/spoke model.

## Operational Governance

- Container image scanning via ACR (Malware/OS vulnerabilities).

- Key rotation policies (NHS Login keys, SMS link signing keys).

- Quarterly access reviews for privileged identities.

## Data Governance

- Data classification of Spectra assets (PII/clinical).

- Data residency in UK South/UK West only.

- Retention rules aligned to DESP/Lung programme requirements.

# Path to Live

This section defines the controlled approach for migrating all Spectra components from on-premises environments into Azure, ensuring operational stability, clinical safety, and alignment with the InHealth Azure Framework, NHS Digital, and NCSC Cloud Security Principles.

## Foundation Readiness (Platform Layer)

Before migrating any workloads, the Azure platform must be fully prepared:

- Hub-and-Spoke architecture complete (VWAN, Palo Alto, HSCN ingress, DNS, Key Vault, Sentinel).

- All Spectra VNets/subnets created for PM, ETL, Portal, Booking, PACS and DMZ.

- Route tables applied per subnet, enforcing forced tunnelling to Palo Alto.

- No NSGs used on application subnets (FWN.02 compliance).

- ACR, Private Endpoints, Private DNS zones deployed.

- Monitoring (Log Analytics, Alerts, Defender for Cloud) operational.

## Proof of Concept (Vertical Slice)

A full vertical slice for a single programme is deployed to validate architecture, performance, image access and workflow interoperability:

Included

- Containerised Spectra PM

- Azure PostgreSQL Flexible Server

- Azure Files Premium ( storage)

- Patient Portal (frontend/backend)

- Instant Booking (optional)

- ETL Service

- PACS Integration Service

- Harmony test VM (synthetic OCT dataset)

- App Gateway + WAF

- Private DNS + PEs + VNet Integration

- Full end-to-end transaction testing

### Objectives

- Validate private routing (Hub → Spoke → PE → DB → Files).

- Validate image performance for graders.

- Validate OCT retrieval via PACS Integration Service.

- Validate security posture (WAF, no public endpoints, private-only PaaS).

- Confirm container hosting and scaling behaviour.

## Non-Production Migration (Dev/Test)

After a successful POC:

- All Dev/Test Spectra PM programmes are containerised and migrated.

- Dev/Test Portal, Booking, ETL and PACS Integration deployed to App Service Plans.

- Non-prod PostgreSQL databases migrated.

- imaging copied to Azure Files Premium (non-prod datasets).

- Clinical workflows tested end-to-end within non-prod.

This ensures the migration process is repeatable for production.

## Production Migration (Programme-by-Programme)

Migration is carried out per programme to maintain isolation and reduce risk.

# Proposed Migration Order

- Lung (Instant Booking + Lung Core)

- DESP/Lung PM Programmes

- Patient Portal

- PACS Integration Service (shared)

- Harmony PACS

Each programme follows the same methodology:

### Deployment Validation:

The InHealth application team must successfully deploy container updates through Dev → Test → Pre-Production environments into Azure App Service before any production cutover. This confirms the team can build, package, configure, and release application updates independently in the new Azure platform.

# Cutover Steps

- Freeze on-prem writes (short downtime)

- Final DB delta sync (on-prem → PostgreSQL Flexible Server)

- Final  file sync (SMB → Azure Files)

- Update DNS: switch API/Portal endpoints to Azure

- Bring Azure services online (App Service, PEs, AppGW)

- Conduct programme-level functional and clinical tests

- Confirm stability before switching off on-prem services

# Rollback

- Revert DNS to on-prem endpoints

- Reactivate on-prem DB as source of truth

- Revert API/Portal endpoints

- For Harmony: revert to previous on-prem snapshot

- Rollback window: 48 hours after cutover

# Post-Go-Live Stabilisation

For each programme:

- Enhanced monitoring for App Service, DB, Files, WAF

- Clinical validation of image viewing, grading, booking

- Autoscale tuning based on real usage

- Error-handling and alerting reviewed with product team

- Performance checks (DB latency, SMB latency, API throughput)

- Stabilisation lasts 2–5 days per programme

# Transition to Business-as-Usual (BAU)

# Operational handover

- Infra team: VWAN, firewalls, AppGW, DNS, PEs, DBs, Files

- App/Dev team: containers, App Service plans, updates

- SOC team: Sentinel, Defender, WAF alerts, audit events

- Support team: first-line triage using dashboards

# DR & Resilience

- PostgreSQL PITR validated

- Azure Files backup via Azure Backup snapshots

- Harmony VM backup + restore tested

- Regional DR (UK West) capability confirmed

# Cost & Resource Optimisation

- Validate App Service plan right-sizing

- Consider scale-to-zero for non-prod (ACA optional)

- Review storage tiering for /OCT data

# Final Migration Completion

Once all programmes, PM workloads, Portal, ETL, Booking, PACS Integration Service and Harmony are migrated and stable:

- Hybrid mode is decommissioned

- All on-prem VMs retired or archived

- Azure becomes the authoritative hosting platform for all Spectra services